## Summery
Development Total |  | 79
Data Base |  | 7
Design |  | 27
Web Servises |  | 30
Documentation |  | 10
Integration(5%) |  | 3.95
Testing
| Development Testing(6%) | 4.74
| QA Testing | 5
Total |  | 166.69
Training | mobile *2 | 72
Total + Training |  | 238.69

## Men Day Estimation
Process | Forms | Mobile | Unit | Web | Implementation | Design Day
Customer Registration | Add Customer | X |  | X | 8 | 1
| Edit Customer | X
| Reset Password | X
| List of Customer |  |  | X
Identification Information | List Identification | X |  |  | 4 | 1
| Edit IDs | X
Search Beer | Near By Map | X |  |  | 8 | 1
| Venue Search | X
| Beer Search | X |  | X
Select Beer | Shopping Card | X | X | X | 5
Edit Beer | Edit | X | X | X | 9 | 0.5
Open Tab | Enter Credit Card Info | X |  |  | 12 | 2
| Edit Credit Card Info | X
| Select Credit Card | X
| submit total charge | X
| Cashier Cash |  |  | X
| Cashier Swipe Card |  |  | X
Barcode reader | Welcome Message |  | X | X | 8 | 2
| Barcode | X
Transaction Finish | Good Bye Message | X | X |  | 11 | 3
Payment | Total Charge till now | X |  |  | 2.5 | 1
Close Tab | Total Charge detail (+ Tax) | X |  | X | 8.5 | 2
| Return Money |  |  | X
Authorization | License Check |  |  | X | 7 | 2
| Manually(Add+ confirm) |  |  | X
Open Shift | Staff Login |  |  | X | 2 | 1
| Enter Cash Drawer Amount |  |  | X
Staff Registration | Add Staff Info |  |  | X | 2 | 1
| Edit Staff Info |  |  | X
| Reset Password |  |  | X
Staff Access Level | Assign Access Level (editable) |  |  | X | 3 | 1
Venue Info | Add Venue |  |  | X | 2 | 1
| Edit Venue |  |  | X
| Delete Venue |  |  | X
Unit Info | Add Unit |  |  | X | 2 | 1
| Edit Unit |  |  | X
| Delete Unit |  |  | X
Beer Info | Add Beer |  |  | X | 3 | 1
| Edit Beer |  |  | X
| Delete Beer |  |  | X
| List Beer |  |  | X
Keg Info | Add Keg |  |  | X | 5 | 2
| Edit Keg |  |  | X
| Delete Keg |  |  | X
| To Archive |  |  | X
| To Deck |  |  | X
| To Tap |  |  | X
Tap Info | Add Tap |  |  | X | 2 | 1
| Edit Tap |  |  | X
| Delete Tap |  |  | X
Maintenance | Put to Maitnance Take out of Maintnance |  |  | X | 1.5 | 0.5
Reports |  |  |  |  | 3.5 | 2
| Emp. time Report |  |  | X
| Daily Total Report |  |  | X
| Tap Remain Report |  |  | X
| Summary Report |  |  | X
| Ounce By patron Report |  |  | X
Total |  |  |  |  | 109 | 27

## Team and Price managment
Members | days per week
Abbas | 5
Navid | 2.5
Omid | 2.5
Sahar | 2.5
Total Per Week | 12.5
Total Project Days | 166.69
Total Project Days + Training |  | 238.69
weeks | 13.3352 | 19.0952
Months | 2.9634 | 4.2434
Total Price (35$) | 46673.2 | 66833.2