## Men Day Details
Process | Forms | Mobile | Unit | Web | Mobile Day | Unit Day | Web Day | Web Service Day | Design Day | Background Process
Customer Registration | Add Customer | X |  | X | 2.5 |  | 1 | 1 | 1
| Edit Customer | X
| Reset Password | X
| List of Customer |  |  | X |  |  | 1
Identification Information | List Identification | X |  |  | 1.5 |  |  | 1 | 1
| Edit IDs | X
Search Beer | Near By Map | X |  |  | 1 |  |  | 1 | 1 | Detect Venue By GPS Default home
| Venue Search | X |  |  | 1
| Beer Search | X |  | X | 1 |  | 1
Select Beer | Shopping Card | X | X | X | 1 | 1 | 1 | 1
Edit Beer | Edit | X | X | X | 0.5 | 7 | 0.5 | 0.5 | 0.5 | If it is on unit it will call the transaction start for flowmetter
Open Tab | Enter Credit Card Info | X |  |  | 2 |  |  | 1 | 2 | In-App purchase Check credit Card Validation Read From Card Reader put payment transaction to pending Assign some credit to the person
| Edit Credit Card Info | X
| Select Credit Card | X
| submit total charge | X |  |  | 1 |  |  | 0.5
| Cashier Cash |  |  | X |  |  | 0.5 | 1
| Cashier Swipe Card |  |  | X |  |  | 3
Barcode reader | Welcome Message |  | X | X |  | 3 | 2 | 1 | 2 | scanner on Unit, Generate code in Server, Pool Next Person Handling (time out, finish, charge done)
| Barcode | X |  |  | 1 |  |  |  |  | Multiple Screen
Transaction Finish | Good Bye Message | X | X |  | 2 | 3 |  | 4 | 3 | Ounce Calculation, Calculate remain Ounce, Send to Flow Metter Check the finish status, Calculate remain ounce Keg/order Remain (Separate Function)
Payment | Total Charge till now | X |  |  | 1 |  |  | 0.5 | 1 | Calculate the total charge place charge on pending
Close Tab | Total Charge detail (+ Tax) | X |  | X | 2.5 |  | 0.5 | 1 | 2 | Calculate Total Debt Charge credit Card
| Return Money |  |  | X |  |  | 2 |  |  | Generate Receipt
Authorization | License Check |  |  | X |  |  | 2 | 2 | 2 | App ID should be the same as DB ID Check the Authorized Flag with time limit
| Manually(Add+ confirm) |  |  | X |  |  | 1 | 2
Open Shift | Staff Login |  |  | X |  |  | 1 | 0.5 | 1
| Enter Cash Drawer Amount |  |  | X |  |  | 0.5
Staff Registration | Add Staff Info |  |  | X |  |  | 1 | 1 | 1
| Edit Staff Info |  |  | X
| Reset Password |  |  | X
Staff Access Level | Assign Access Level (editable) |  |  | X |  |  | 1 | 2 | 1 | Select and check all permisions
Venue Info | Add Venue |  |  | X |  |  | 1 | 1 | 1 | including Time Limit and Consumption Limit
| Edit Venue |  |  | X
| Delete Venue |  |  | X
Unit Info | Add Unit |  |  | X |  |  | 1 | 1 | 1 | Including Per Pour Limit
| Edit Unit |  |  | X
| Delete Unit |  |  | X
Beer Info | Add Beer |  |  | X |  |  | 1 | 2 | 1
| Edit Beer |  |  | X
| Delete Beer |  |  | X
| List Beer |  |  | X
Keg Info | Add Keg |  |  | X |  |  | 1 | 1 | 2 | Set Alarm If less than amount
| Edit Keg |  |  | X
| Delete Keg |  |  | X
| To Archive |  |  | X |  |  | 0.5 | 1.5
| To Deck |  |  | X |  |  | 0.5
| To Tap |  |  | X |  |  | 0.5
Tap Info | Add Tap |  |  | X |  |  | 1 | 1 | 1
| Edit Tap |  |  | X
| Delete Tap |  |  | X
Maintenance | Put to Maitnance Take out of Maintnance |  |  | X |  |  | 1 | 0.5 | 0.5 | Which Tap on maintanace Close Tap
Reports
| Emp. time Report |  |  | X |  |  | 0.5 | 1 | 2
| Daily Total Report |  |  | X |  |  | 0.5
| Tap Remain Report |  |  | X |  |  | 0.5
| Summary Report |  |  | X |  |  | 0.5
| Ounce By patron Report |  |  | X |  |  | 0.5
Total |  |  |  |  | 18 | 14 | 29 | 30 | 27